## general_report
PI6 Features | [9 empty] | Story # | Story Summary | owner | 0
Summary | Key | Updated | Created | Status | Assignee | Component/s | PI | Story Points | Reporter
Entity Broker 2.0 | DTNATELE-9461 | 2019-10-07 21:44 | 2019-10-07 21:25 |  | Jeffrey Shelton | Detroit Connect Portal, Entity Broker | PI6 |  | Corey DeMarco
Detroit Connect Portal: Vehicle List Page - Phase 1 | DTNATELE-9460 | 2019-10-07 21:45 | 2019-10-07 21:21 |  | Jeffrey Shelton | Detroit Connect Portal | PI6 |  | Corey DeMarco
VT Sunset: Customer migration | DTNATELE-9380 | 2019-10-05 00:43 | 2019-10-04 18:11 |  | Brandon Atnip | Detroit Connect Portal | PI6 | L-XL | Brandon Atnip | TBD | Story breakdown to occur between Corey, Brandon, Jeff | BE | Determine migration timeline and how many customers can be migrated at a time. Dependent on SF
TBD
TBD
VT Sunset: Express WriteUp endpoints | DTNATELE-9379 | 2019-10-05 00:50 | 2019-10-04 18:08 |  | Brandon Atnip | Detroit Connect Portal | PI6 | TBD per discovery | Brandon Atnip |  | Per Jacob Express Writeup is searching by VIN and date range for fault history currently (25-30K calls per week). We need to expose an endpoint in Entity Broker 2.0 that Express Writeup can consume… |  | Additional discovery needed. Brandon to follow up with Jacob
[7 empty] | PI6 |  |  |  | Add more stories after getting more info from Marty K.
VT Sunset: DCP Alerts | DTNATELE-9378 | 2019-10-05 00:39 | 2019-10-04 18:07 |  | Brandon Atnip | Detroit Connect Portal | PI6 | 2 | Brandon Atnip | TBD | System notifications (monitor Azure data points; expand current Azure monitoring) | BE
VT Sunset: DCP Reporting | DTNATELE-9377 | 2019-10-05 00:33 | 2019-10-04 18:07 |  | Brandon Atnip | Detroit Connect Portal | PI6 | 3 | Brandon Atnip | TBD | Writing fault notification from Storm into Azure (Tableau reports, pulling fault info from Hbase) | BE
VT Sunset: Feedback/issues | DTNATELE-9376 | 2019-10-05 00:29 | 2019-10-04 18:03 |  | Brandon Atnip | Detroit Connect Portal | PI6 | TBD talk to Lauren | Brandon Atnip | TBD | Placeholder #1 with low story points for dealer feedback during pilot |  | creating bandwidth
[10 empty] | TBD | Placeholder #2 with low story points for dealer feedback during pilot
VT Sunset: Notification monitoring | DTNATELE-9375 | 2019-10-05 00:23 | 2019-10-04 18:01 |  | Brandon Atnip | Detroit Connect Portal | PI6 | Mahesh to size | Brandon Atnip | TBD | Fault logging in VT Dash | BE
[8 empty] | 3 |  | TBD | Log comparison between VT and DCP | BE
VT Sunset: DCP flag or role | DTNATELE-9374 | 2019-10-04 22:47 | 2019-10-04 17:58 |  | Brandon Atnip | Detroit Connect Portal | PI6 | Lloyd recommended SSO a-c stories | Brandon Atnip |  | SSO work for non-Azure | BE
[7 empty] | PI6 | 2 |  | TBD | SSO a. - provision unwrapped JWT token for difference inspection between dealer and fleet users
[7 empty] | PI6 | 8 |  | TBD | SSO b. - update authorization path to include specific NONCE value
[7 empty] | PI6 | 2 |  | TBD | SSO c. - update authorization path to include specific redirect URL
[7 empty] | PI6 | 0 |  | TBD | DTNAConnect/OnePortal Update
VT Sunset: User Guides | DTNATELE-9373 | 2019-10-04 22:40 | 2019-10-04 17:32 |  | Brandon Atnip | Detroit Connect Portal | PI6 | S | Jeffrey Shelton | 9676 | User guide | Karen
[7 empty] | PI6 | S |  | 9692 | UX
[7 empty] | PI6 | S |  | 9691 | Guide - VT
[7 empty] | PI6 | 1 |  | 9689 | Guide - Notification | FE
[10 empty] | TBD | Add PDF |  | UI
Service Center Indication for 3rd Party Vendor | DTNATELE-9372 | 2019-10-04 16:00 | 2019-10-04 16:00 |  | Jeffrey Shelton |  | PI6 |  | Jeffrey Shelton
Fault Ingest for 3rd Party Vendors | DTNATELE-9371 | 2019-10-04 22:28 | 2019-10-04 15:58 |  | Jeffrey Shelton |  | PI6 |  | Jeffrey Shelton
VIN Validation | DTNATELE-9346 | 2019-10-04 22:53 | 2019-10-04 01:01 |  | Paula Swinyard |  | PI6 |  | Meagan Phillips
UI Updates for 3rd Party Vendor | DTNATELE-9344 | 2019-10-04 16:00 | 2019-10-04 00:50 |  | Jeffrey Shelton |  | PI6 | 5 | Dorothy Love | 9344 | Cummins UI |  | dealer and flag
[7 empty] | PI6 |  |  | 9371 | Cummins fault ingest
XL
[7 empty] | PI6 | 13 |  | 9372 | Cummins service center |  | Getting data from SSI
[7 empty] | PI6 |  |  | TBD | Data segragation
[7 empty] | PI6 |  |  | TBD | Monitoring
Detroit Connect Portal: Vehicle List Page - Phase 2 | DTNATELE-9343 | 2019-10-07 21:41 | 2019-10-03 23:45 |  | Jeffrey Shelton | Detroit Connect Portal | PI6 |  | Michelle McConn |  | Scalability: Vehicle List Page
Integrating EconicSD into DC Portal | DTNATELE-9338 | 2019-10-04 15:41 | 2019-10-03 22:31 |  | Jeffrey Shelton | Detroit Connect Portal | PI6 |  | Jeffrey Shelton | 9339 | Block OTA |  | Done?
[7 empty] | PI6 | 1 |  | 9340 | Add indicator for Econic vehicles |  | Update IMS DB codes ; dependency on team 1 for DB codes from Isaac
[7 empty] | PI6 | 13 |  | 9341 | Flag Econic Certified dealers & automation |  | NPS; add attribute to fault table
[7 empty] | PI6 | 3 |  | TBD | UI work to find closest Econic dealers
Add message banner to DCP | DTNATELE-7487 | 2019-10-04 22:30 | 2019-07-15 20:45 |  | Jeffrey Shelton |  | PI6 | 8 | Jeffrey Shelton | 7720 | Create BE Table and read/write/delete endpoints
[7 empty] | PI6 | 5 |  | 7721 | UI display on sign-in page
[7 empty] | PI6 | 5 |  | TBD | UI for data entry
[7 empty] | PI6 | 2 |  | TBD | Create new Ops role to update vehicle/fleet contacts (Managed vehicle page; admin access and user everywhere else
Deactivate VINs from Dynamic Lease | DTNATELE-5362 | 2019-10-04 19:30 | 2019-03-21 17:27 |  | Paula Swinyard |  | PI5/PI6 |  | Meagan Phillips
Activate VINs for Dynamic Lease | DTNATELE-5361 | 2019-10-04 22:57 | 2019-03-21 17:25 |  | Paula Swinyard |  | PI5/PI6 |  | Meagan Phillips
Email Notifications for SN, SS, and SI | DTNATELE-3571 | 2019-10-04 22:21 | 2019-01-25 00:28 |  | Jeffrey Shelton | Detroit Connect Portal, Notification | PI6 |  | Michelle McConn | 1796 | Backend |  | M for templates
[7 empty] | PI6 | 13 |  | 7971 | 4 templates |  | Topology in 1414. Still needed?
Implement Single Sign In functionality for Dealers. | DTNATELE-2747 | 2019-10-04 22:51 | 2019-01-08 17:30 |  | Jeffrey Shelton |  | PI5/PI6 |  | Michelle McConn | 145 | SSO: Prompt dealers to use DTNAConnect SSO
[7 empty] | PI6 |  |  | 146 | SSO: Enable Dealer Sign-In through DTNAConnect
PI6
Finder - Serial Number Search | DTNATELE-1428 | 2019-10-04 22:09 | 2018-10-26 23:03 |  | Jeffrey Shelton | Detroit Connect Portal | PI6 | 3 | Michelle McConn | 7973 | Search by SN end point | BE | Endpoint: Serial search
[7 empty] | PI6 | 3 |  | 9560 | Read end point to update SN search history | BE | Endpoint: Read/Write
[7 empty] | PI6 | 5 |  | 5092 | Endpoint: Discovery (Write end point to update SN search history) | BE | Endpoint: Discovery
[7 empty] | PI6 | 5 |  | 5861 | UI - serial and update search history | FE | UI for Finder > SN
[7 empty] | PI6 | 2 |  | 9561 | UI - update how we getting current search history | FE | UI to update how updating search history
Fault Notification: Fleet/Role Level Setting - Configure Individual Faults | DTNATELE-1416 | 2019-10-04 00:44 | 2018-10-26 19:49 |  | Jeffrey Shelton | Detroit Connect Portal | PI5/PI6 |  | Michelle McConn | 7968
[7 empty] | PI6 |  |  | 7970
Fault Notification - Fleet/Role Level Settings - Service Now, Service Soon, Service Info | DTNATELE-1415 | 2019-10-04 00:33 | 2018-10-26 19:46 |  | Jeffrey Shelton | Detroit Connect Portal | PI5/PI6 |  | Michelle McConn
[7 empty] | PI6 |  |  | 7967
Backend Framework for Notification | DTNATELE-1414 | 2019-10-04 22:02 | 2018-10-26 19:42 |  | Jeffrey Shelton | Detroit Connect Portal, Entity Broker | PI5/PI6 | L | Michelle McConn | 7330 | Hooking up topology
Fault Code Manager | DTNATELE-139 | 2019-10-04 22:17 | 2018-09-12 20:34 |  | Jeffrey Shelton |  | PI6 | 2 | Michelle McConn | 2801 | Implement Fault Code Management Page |  | Teletable
[7 empty] | PI6 | 1 |  | 2802 | Implement Fault Content Management |  | Edit Fault Notes modal
[7 empty] | PI6 | 13 |  | 2804 | Front-end Upload Fault Code CSV - vehicle config | UI | CSV uploads + modal
[7 empty] | PI6 | 8 |  | TBD | UI - Upload CSV - fault code |  | FE to convert CSV to list of JSON objects and BE consume and put where it needs to go (on new framework)
[7 empty] | PI6 | 3 |  | 2808 | Test Email for a VT Fault
[7 empty] | PI6 | 2 |  | 2811 | Fault Content Preview
[7 empty] | PI6 |  |  | 2819 | Back-end work for Upload Fault Code CSV | BE
[7 empty] | PI6 | 13 |  | TBD | BE work for vehicle confi
[7 empty] | PI6 |  |  | 2896 | Implement Email Templates to apply to a Test Email |  | Obsolete?
PI5 Features
Summary | Key | Updated | Created | Status | Assignee | Component/s | PI | Story Points | Reporter
Manage Vehicles: Action Functionality | DTNATELE-7646 | 2019-09-30 18:58 | 2019-07-22 17:12 |  | Jeffrey Shelton |  | PI5 |  | Jeffrey Shelton
Manage Vehicles: Services | DTNATELE-7486 | 2019-08-06 22:57 | 2019-07-15 17:45 |  | Jeffrey Shelton |  | PI5 |  | Jeffrey Shelton
Incorporate Image Library into VT | DTNATELE-7139 | 2019-08-06 23:05 | 2019-06-20 16:47 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Customer Journey: Detroit Connect Portal Changes | DTNATELE-7124 | 2019-10-04 19:55 | 2019-06-20 00:30 |  | Unassigned | CMS | PI5 |  | Paula Swinyard
Manage Vehicles: Page Layout | DTNATELE-7104 | 2019-08-15 22:43 | 2019-06-19 22:10 |  | Jeffrey Shelton |  | PI5 |  | Jeffrey Shelton
Registration: Save Functionality | DTNATELE-6847 | 2019-08-06 22:49 | 2019-06-04 18:32 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Registration: Fleet Contact List | DTNATELE-6846 | 2019-08-06 22:49 | 2019-06-04 18:31 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Registration; Admin and Tech Support | DTNATELE-6845 | 2019-08-06 22:49 | 2019-06-04 18:31 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Registration: Customer Information | DTNATELE-6843 | 2019-08-06 22:49 | 2019-06-04 18:30 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Refactor: Registration | DTNATELE-6837 | 2019-08-06 22:49 | 2019-06-04 18:10 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Refactor: Settings > Profile Information | DTNATELE-6771 | 2019-08-12 18:18 | 2019-05-30 20:55 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Manage Vehicles: Unit ID | DTNATELE-6722 | 2019-08-06 22:48 | 2019-05-28 19:51 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Vehicle List Page Updates | DTNATELE-6543 | 2019-08-12 18:16 | 2019-05-16 18:21 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Refactor: Service Center Details | DTNATELE-6204 | 2019-05-02 21:13 | 2019-05-01 19:44 |  | Michael Guida |  | PI5 |  | Jeffrey Shelton
QA Automation Framework | DTNATELE-6086 | 2019-05-01 20:40 | 2019-04-23 23:28 |  | Unassigned |  | PI5 |  | Ori Applebaum
Create Event Hub for the CSC ticket to be created | DTNATELE-5937 | 2019-06-21 18:48 | 2019-04-17 20:43 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Michelle McConn
GA: User Logins by Email | DTNATELE-5911 | 2019-04-22 19:05 | 2019-04-17 00:33 |  | Unassigned |  | PI5 |  | Shawna Ionita
VT Upgrade Hardening | DTNATELE-5832 | 2019-06-20 00:14 | 2019-04-15 20:57 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Fault Notification: Fleet/Role Level Setting - By Category | DTNATELE-5785 | 2019-04-22 19:04 | 2019-04-12 19:19 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Michelle McConn
Account for Source Address and vehicle information upon Fault decoding. | DTNATELE-5551 | 2019-09-23 18:13 | 2019-04-01 23:58 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Erik Stone
Finder - Engine Serial Number | DTNATELE-5023 | 2019-07-23 06:24 | 2019-03-05 18:27 |  | Jeffrey Shelton |  | PI5 |  | Jeffrey Shelton
Align Event ID to be the same for VT and Portal | DTNATELE-4892 | 2019-03-16 | 2019-02-27 00:08 |  | Unassigned |  | PI5 |  | Michelle McConn
Portal Notifications Inbox UI | DTNATELE-3432 | 2019-07-19 18:32 | 2019-01-23 22:55 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Michelle McConn
DC Portal - Track User Behavior Between Pages | DTNATELE-3287 | 2019-07-23 01:15 | 2019-01-22 01:50 |  | Brandon Atnip |  | PI5 |  | Shawna Ionita
GA: DC Portal Page Load Time Metric | DTNATELE-3284 | 2019-07-23 01:05 | 2019-01-22 00:51 |  | Brandon Atnip |  | PI5 |  | Shawna Ionita
GA: DC Portal Login Metric | DTNATELE-3280 | 2019-06-21 18:45 | 2019-01-22 00:38 |  | Daniel Mesquita |  | PI5 |  | Shawna Ionita
Portal Admin & User Metrics: GA Default Dimensions | DTNATELE-3135 | 2019-04-30 18:41 | 2019-01-17 21:05 |  | Shawna Ionita | Detroit Connect Portal | PI5 |  | Shawna Ionita
Assets > Email Templates Library | DTNATELE-2876 | 2019-02-26 16:45 | 2019-01-10 21:04 |  | Unassigned | Detroit Connect Portal | PI5 |  | Michelle McConn
Manage Vehicles: Vehicle Contacts | DTNATELE-2542 | 2019-06-17 21:23 | 2018-12-22 01:11 |  | Unassigned | Detroit Connect Portal | PI5 |  | Jeffrey Shelton
Finder - Recent Search - Event ID | DTNATELE-2374 | 2019-04-16 14:48 | 2018-12-12 18:07 |  | Unassigned | Detroit Connect Portal | PI5 |  | Jeffrey Shelton
Fault Export Functionality | DTNATELE-2371 | 2019-02-01 20:48 | 2018-12-12 06:37 |  | Shivani Thakar |  | PI5 |  | Jeffrey Shelton
Migrate VSO Portal API Code to GSEP | DTNATELE-1845 | 2019-02-01 20:37 | 2018-11-13 00:01 |  | Unassigned |  | PI5 |  | Michelle McConn
Web Analytics for Vehicle Landing Page | DTNATELE-1704 | 2019-02-01 20:50 | 2018-11-08 21:24 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Migrate VSO iOS Code to GSEP | DTNATELE-1604 | 2019-02-01 20:53 | 2018-11-05 18:53 |  | Unassigned |  | PI5 |  | Clinton Pereira
Migrate VSO Android Code to GSEP | DTNATELE-1603 | 2019-01-29 21:53 | 2018-11-05 18:52 |  | Unassigned |  | PI5 |  | Clinton Pereira
Refactor: Event Diagnosis | DTNATELE-1504 | 2019-05-04 01:49 | 2018-10-31 17:32 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Jeffrey Shelton
Refactor: Fault Event Inbox | DTNATELE-1503 | 2019-02-01 20:52 | 2018-10-31 17:31 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
Activity Notification - Pending signup request | DTNATELE-1478 | 2019-02-14 23:54 | 2018-10-30 22:44 |  | Unassigned |  | PI5 |  | Michelle McConn
Activity Notifications - DCD | DTNATELE-1476 | 2019-02-14 23:53 | 2018-10-30 22:41 |  | Unassigned |  | PI5 |  | Michelle McConn
Activity Notifications - xOTA | DTNATELE-1474 | 2019-02-14 23:52 | 2018-10-30 22:39 |  | Unassigned |  | PI5 |  | Michelle McConn
Safety Event Notifications | DTNATELE-1473 | 2019-02-14 23:51 | 2018-10-30 22:34 |  | Unassigned |  | PI5 |  | Michelle McConn
System Admin Notification | DTNATELE-1418 | 2019-03-01 20:17 | 2018-10-26 19:59 |  | Unassigned | Detroit Connect Portal, Notification | PI5 |  | Michelle McConn
Migrate VSO Portal Front End Code to GSEP | DTNATELE-1173 | 2019-02-01 20:34 | 2018-10-18 00:29 |  | Unassigned |  | PI5 |  | Clinton Pereira
Refactor - Vehicle History - Faults | DTNATELE-842 | 2019-02-26 00:29 | 2018-10-04 22:58 |  | Jeffrey Shelton |  | PI5 |  | Michelle McConn
Refactor Settings - Manage Users and Roles | DTNATELE-701 | 2019-04-09 18:21 | 2018-10-02 20:25 |  | Marri Gamard |  | PI5 |  | Michelle McConn
Automation of Operations | DTNATELE-556 | 2019-02-01 20:35 | 2018-09-26 00:39 |  | Unassigned |  | PI5 |  | Jeffrey Shelton
PoC of the SSO functionality | DTNATELE-280 | 2019-05-20 18:37 | 2018-09-21 19:35 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Michelle McConn
Finder - Recent Search - VIN | DTNATELE-278 | 2019-03-28 19:03 | 2018-09-21 19:31 |  | Unassigned |  | PI5 |  | Michelle McConn
Assets > Image Library | DTNATELE-140 | 2019-06-21 18:44 | 2018-09-12 20:37 |  | Jeffrey Shelton | Detroit Connect Portal | PI5 |  | Michelle McConn
Event Diagnosis Updates | DTNATELE-138 | 2019-08-02 00:05 | 2018-09-12 20:32 |  | Tyler Miller |  | PI5 |  | Michelle McConn
Vehicle History Updates | DTNATELE-137 | 2019-03-06 15:52 | 2018-09-12 20:28 |  | Unassigned | Detroit Connect Portal | PI5 |  | Michelle McConn
Finder - Event ID search | DTNATELE-136 | 2019-04-16 14:51 | 2018-09-12 20:24 |  | Unassigned | Detroit Connect Portal | PI5 |  | Michelle McConn
Create/Delete CS Agents | DTNATELE-135 | 2019-03-18 17:33 | 2018-09-12 20:22 |  | Unassigned |  | PI5 |  | Michelle McConn
Create/Delete CS Admins | DTNATELE-134 | 2019-04-16 14:36 | 2018-09-12 20:17 |  | Unassigned |  | PI5 |  | Michelle McConn
Finder - VIN Search | DTNATELE-133 | 2019-03-11 17:10 | 2018-09-12 20:13 |  | Unassigned |  | PI5 |  | Michelle McConn
CS Admin and CS Agent sign in/out functionality | DTNATELE-132 | 2019-03-06 16:26 | 2018-09-12 20:03 |  | Unassigned | Detroit Connect Portal | PI5 |  | Michelle McConn
VT Dash New User Types | DTNATELE-131 | 2019-02-13 21:16 | 2018-09-12 19:46 |  | Unassigned |  | PI5 |  | Michelle McConn
Generated at Wed Oct 09 16:22:43 CEST 2019 by Amy Peradotta using Jira 7.13.8#713008-sha1:1606a5c1e7006e1ab135aac81f7a9566b2dbc3a6.
Note on I5: Peradotta, Amy (164-Extern): potentially 3, 20pt. Stories. Our work is done, dependency is on SF replacement of Remedy
Note on L5: Peradotta, Amy (164-Extern): Determining what notifications exist, what fleets exist, terms and conditions, and move to Portal
Note on I15: Peradotta, Amy (164-Extern): Mahesh confirmed we are logging VT notifications in the system with the following fields: Customer information, Vehicle information, Sent notification email id, Remedy ticket#, Notification timestamp. Corey confirmed no more are needed.